## Sheet1
| Running Total |  |  | Total Estimate |  |  |  | Start Date | 2018-09-15
Direct Labor: | [7 empty] | Today | 2018-10-10
Category or individual: | Rate/Hr | Hrs |  | Rate/Hr | Hrs |  |  | End Date | 2018-12-01
Christian | 18 | 37 | 666 | 18 | 150 | 2700 | Notes:
John | 18 | 30 | 540 | 18 | 150 | 2700
Zach | 18 | 40 | 720 | 18 | 150 | 2700
Zarka | 18 | 42 | 756 | 18 | 150 | 2700
Total Labor: |  |  | 1926 |  |  | 8100
Direct Labor Cost: |  | Subtotal: | 1926 |  | Subtotal: | 8100
Indirect Labor Cost | rate: | 100% | 1926 | rate: | 100% | 8100
Total Direct Labor: |  |  | 3852 |  |  | 16200
Supplies And Materials: |  |  | 387.02 |  |  | 0
(from Materials Cost worksheet)
Total Direct Material Cost: |  |  | 387.02 |  |  | 0
Equipment Rental: | Value | Rental Rate (Per Week) |  | Value | Rental Rate |  | Date begin | Today/End Date | Total days
Oscilloscope | 2851 | 1% | 313.61 | 2851 | 1% | 313.61 | 2018-09-15 | 2018-12-01 | 77
Function Generator | 292.5 | 1% | 32.175 | 292.5 | 1% | 32.175 | 2018-09-15 | 2018-12-01 | 77
DMM | 259 | 1% | 28.49 | 259 | 1% | 28.49 | 2018-09-15 | 2018-12-01 | 77
Power Supply | 699 | 1% | 76.89 | 699 | 1% | 76.89 | 2018-09-15 | 2018-12-01 | 77
Total Rental Costs: |  |  | 451.165 |  |  | 451.165
Total Supplies Materials & Equipment: |  |  | 838.185 |  |  | 451.165
Total TDL+TCL+TDM+TRM |  |  | 4690.185 |  |  | 16651.165
Business Overhead: |  | 55% | 2579.6018 |  | 55% | 9158.1408
[7 empty] | Amount Under: |  | 18539.519
Total Cost: |  | Current | 7269.7868 |  | Estimate | 25809.3057 | Amount Over: |  | -18539.519

## Materials Cost
Item | Cost | Quantity | Notes/Website | Purchase date | Total | Part Number | Total Cost
Instrumentation Amplifier | 69 | 1 | Mouser.com |  | 69 | AD624 | Total Cost
Operational Amplifier | 0.41 | 2 | Mouser.com |  | 0.81 | LM324 | 387.02
Phototransistor | 0.44 | 1 | Mouser.com |  | 0.44 | WP3DP3BT
MCUs for Devices | $.99-5.00 | 6 | TBD |  | 30 | TBD
Pushbutton Apem Isr3Sad600 | 15.6 | 1 | Mouser.com |  | 15.6 | 25H7937
12V DC Electric door strike | 15.64 | 1 | Banggood.com |  | 15.64
SainSmart 2-Channel 5V Relay Module | 8.99 | 1 | Amazon.com |  | 8.99
Zigbee Modules | 17.5 | 5 | Mouser.com |  | 87.5 | XB24CZ7PIT-004
MCU Development Kit | $25-30 | 2 | TBD |  | 60
Gereen Board Order | 30 | 2 | Stockroom |  | 60
Interface Dev. Tool USB to Serial | 1.95 | 1 | Mouser.com |  | 1.92 | 713-31799027
LM7341MF/NOPB | 2.56 | 2 | Mouser.com |  | 5.12
Wires for testing | 12 | 1 | Amazon.com |  | 12
Miscellaneous | 20 |  |  |  | 20