## Sheet1
[6 empty] | Zigbee Network Working w/ Simple Devices |  |  | BioMed Circuitry and Code Built
Task | Lead | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11
Hardware |  | Week 1: #REF! | NAMES
Biomedical System | ZE | [11 empty] | ZE | Zach Eakerns
Research and Build Simulations | ZE | Week 1: 100% | JS | John Satterla
Test Simulations | ZE | Week 2: 100% | CJ | Christian Jensen
Create Circuit and Debug | ZE | Week 4: 15% | ZM | Zarka McClung
Test and Debug With Code | ZE | bar: BioMed Circuitry and Code Built Week 8 to BioMed Circuitry and Code Built Week 11
Wireless Communication | JS
Choose Hardware | JS | Week 1: 100%
Order Hardware/Dev. Kits | JS | Week 2: 100%
Interface ZB Modules w/ MCU | JS | Week 4: 20% |  | Incomplete
Design PCBs | JS | [12 empty] | Complete
Test and Debug PCBs | JS | [12 empty] | In Progress
Location Detection | JS | [12 empty] | To Do
Choose Hardware | JS | Week 1: 50% |  | N/A
Order Hardware/Dev. Kits | JS | Week 4: 50%
Test and Debug PCBs | JS
Door Lock System | ZM
Choose Computer type | ZM | Week 1: 100%
Order Hardware | ZM | Week 3: 40%
Build Lock circuit | ZM
Test and Debug with Code | ZM
Software | bar: Week 1 to Zigbee Network Working w/ Simple Devices Week 5; BioMed Circuitry and Code Built Week 9 to BioMed Circuitry and Code Built Week 11
Code for Biomedical Systems | ZE
Research | ZE | Week 3: 70%
Write and Debug | ZE | Week 4: 20%
Test and Debug with Circuit | ZE | bar: BioMed Circuitry and Code Built Week 8 to BioMed Circuitry and Code Built Week 11
Voice Control | CJ
Research | CJ | Week 3: 90%
Speech Recognition Code | CJ | Week 4: 50%
Speech Control | CJ
Test and debug | CJ
Wireless Communication | JS
Research | JS | Week 1: 100%
Create Zigbee Network Protocol | JS
Test Network w/ 5+ Devices | JS
Test and debug | JS
Location Detection | JS
Research | JS | Week 1: 75%
Interface with Mobile System MCU | JS
Write and Test Algorithm | JS
Test and debug | JS
Facial Recognition | ZM
Research | ZM | Week 1: 80%
Choose Algorithm for solution | ZM | Week 3: 70%
Use Algorithm to write code | ZM | Zigbee Network Working w/ Simple Devices Week 5: 50%
Detect Faces | ZM | bar: Week 1 to Week 4; Zigbee Network Working w/ Simple Devices Week 6; BioMed Circuitry and Code Built Week 11
Integrate it with Door | ZM | bar: Week 1 to Zigbee Network Working w/ Simple Devices Week 5; BioMed Circuitry and Code Built Week 8 to BioMed Circuitry and Code Built Week 11
Test and debug | ZM
Complete Face Detection